PRACTICAL 4

Estimation of Project Metrics

Objective

Categorize projects using COCOMO, and estimate effort and development time required for a project

Estimate the program complexity and effort required to recreate it using Halstead's metrics

Aim: To understand how to estimate key project parameters such as size, cost, duration, and effort using two established techniques: COCOMO (Constructive Cost Model) and Halstead’s complexity metrics. These estimations help in selecting suitable solution strategies and in effective project planning.

Introduction

After gathering all the requirements specific to the software project, we usually need to think about different solution strategies for the project. Expert business analysts are analyzing their benefits as well as their shortcomings using the cost, time, and resources required to develop them. In this experiment, we will learn how to estimate the cost, effort, and duration of a software project and then select one solution approach that will be found suitable to fulfill the organizational goal.

Project Estimation Techniques

A software project is not just about writing a few hundred lines of source code to achieve a particular objective. The scope of a software project is comparatively quite large, and such a project could take several years to complete. However, the phrase “quite large” could only give some (possibly vague) qualitative information. As in any other science and engineering discipline, one would be interested to measure how complex a project is. One of the major activities of the project planning phase, therefore, is to estimate various project parameters in order to take proper decisions. Some important project parameters that are estimated include:

- Project size: What would be the size of the code written say, in number of lines, files, modules?

- Cost: How much would it cost to develop a software? A software may be just pieces of code, but one has to pay to the managers, developers, and other project personnel.

- Duration: How long would it be before the software is delivered to the clients?

- Effort: How much effort from the team members would be required to create the software?

In this experiment we will focus on two methods for estimating project metrics: COCOMO and Halstead’s method.

COCOMO

COCOMO (Constructive Cost Model) was proposed by Boehm. According to him, there could be three categories of software projects: organic, semidetached, and embedded. The classification is done considering the characteristics of the software, the development team and environment. These product classes typically correspond to application, utility and system programs, respectively. Data processing programs could be considered as application programs. Compilers, linkers, are examples of utility programs. Operating systems, real-time system programs are examples of system programs. One could easily apprehend that it would take much more time and effort to develop an OS than an attendance management system.

The concept of organic, semidetached, and embedded systems are described below.

- Organic: A development project is said to be of organic type, if

  - The project deals with developing a well understood application

  - The development team is small

  - The team members have prior experience in working with similar types of projects

- Semidetached: A development project can be categorized as semidetached type, if

  - The team consists of some experienced as well as inexperienced staff

  - Team members may have some experience on the type of system to be developed

- Embedded: Embedded type of development project are those, which

  - Aims to develop a software strongly related to machine hardware

  - Team size is usually large

Halstead’s Complexity Metrics

Halstead took a linguistic approach to determine the complexity of a program. According to him, a computer program consists of a collection of different operands and operators. The definition of operands and operators could, however, vary from one person to another and one programming language to other. Operands are usually the implementation variables or constants – something upon which an operation could be performed. Operators are those symbols that affects the value of operands. Halstead’s metrics are computed based on the operators and operands used in a computer program. Any given program has the following four parameters:

- n1: Number of unique operators used in the program

- n2: Number of unique operands used in the program

- N1: Total number of operators used in the program

- N2: Total number of operands used in the program

Using the above parameters one compute the following metrics:

- Program Length: N=N1+N2

- Program Vocabulary: n=n1+n2

- Volume: V=N×lg n

- Difficulty: D=(n1×N2)/(2×n2)

- Effort: E=D×V

- Time to Implement: T=E/18 (in seconds)

The program volume V is the minimum number of bits needed to encode the program. It represents the program’s size while considering the programming language. The difficulty metric indicates how difficult a program is to write or understand. Effort denotes the “mental effort” required to develop the software or to recreate the same in another programming language.